| # Show Schedule |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date: |  |  |  |  |  |  |  |
| ## Period | ## Mon | ## Tue | ## Wed | ## Thu | ## Fri | ## Sat | ## Sun |
| ### -11 week |  |  |  |  |  |  | Production Mtg 7 PM |
| ### -10 week |  |  |  |  |  |  |  |
| ### -9 week |  |  |  |  |  |  | Production Mtg 7 PM |
| ### -8 week |  |  |  |  |  |  | Prod Mtg 5:30 Auditions 7PM |
| ### -7 week | Auditions 7PM |  |  |  |  |  | Prod Mtg 5:30 Rehearsal |
| ### -6 week | Rehearsal | Rehearsal | Bios due Prod |  |  |  | Rehearsal Bios due Prod |
| ### -5 week | Rehearsal | Rehearsal |  |  | Ads due Peter | End OldShow | Strike OldShow Rehearsal |
| ### -4 week | Rehearsal StageWrite | Rehearsal | Rehearsal Directors Note | Rehearsal | Directors note Due Peter | Set Build 10-5 | Set Build 1-5 Rehearsal Prod Mtg 5:30 |

| # Show Schedule |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date: |  |  |  |  |  |  |  |
| ## Period | ## Mon | ## Tue | ## Wed | ## Thu | ## Fri | ## Sat | ## Sun |
| ### -3 week | Rehearsal Bios Due | Rehearsal | Rehearsal Playbill proof due | Rehearsal |  | Set Build 10-5 | Set Build 1-5 |
| ### -2 week | Rehearsal Playbill 2 Printer | Rehearsal | Rehearsal | Rehearsal |  | Set Build 10-5 Dry Tech | Wet Tech Rehearsal |
| ### -1 week | Rehearsal | Open Dress 8PM | Premier Night Show 8PM | Opening Night Show 8PM | Show 8PM | Set Build 10-5 | Set Build 1-5 Rehearsal |
| ### 1st week | Rehearsa | Open Dress 8PM | Premier NIght Show 8PM | Show 8PM | Show 8PM | Evening 8PM |  |
| ### 2nd week |  |  | Show 8PM | Show 8PM | Show 8PM | Matinee 2PM Evening 8PM |  |
| ### 3rd week |  |  | Show 8PM | Show 8PM | Show 8PM | Matinee 2PM Evening 8PM |  |
| ### 4th week |  |  | Show 8PM | Show 8PM | Show 8PM | Matinee 2PM Evening 8PM |  |
| ### 5th week |  |  | Show 8PM | Show 8PM | Show 8PM | Matinee 2PM Evening 8PM | Strike |